## Hours on user stories
Nr/ID | Description | <HuyT> | <HuyC> | <Nam> | <Linh> | Total
|  | 42 | 41 | 45 | 44 | 172
Sprint 0 | [5 empty] | 0
1 | Make timesheet |  | 3 |  |  | 3
2 | Make Project Plan |  | 4 |  | 2 | 6
3 | Make Project backlog | 3 |  | 2 | 2 | 7
Sprint 1 | [5 empty] | 0
| App present user with code challenge and answer choices | 4 | 4 | 8 | 8 | 24
| Answers are sent to the system for validation | 6 | 3 | 6 | 4 | 19
| System store users with correct answer | 4 | 4 | 6 | 4 | 18
| System present the contact info form to fill in | 6 | 4 | 4 | 4 | 18
Sprint 2 | [5 empty] | 0
| Administrator login | 8 | 6 | 8 | 10 | 32
| Present the GDPR information | 5 | 6 | 5 | 4 | 20
| Show videos of Takeaway.com | 2 | 3 | 2 | 2 | 9
| Improve appearance of application | 4 | 4 | 4 | 4 | 16
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Hours on overhead
Description of the task | <HuyT> | <HuyC> | <Nam> | <Linh> | Total
| 72 | 70 | 74 | 71 | 287
Week 1 |  |  |  |  | 0
Draft project plan |  | 4 |  |  | 4
Time Sheet |  | 3 |  | 2 | 5
Create backlog | 3 |  | 2 | 2 | 7
Week 2 |  |  |  |  | 0
Coding the application | 4 | 4 | 8 | 8 | 24
Working on documentation | 6 | 6 | 3 | 3 | 18
Week 3 |  |  |  |  | 0
Coding the application | 6 | 4 | 6 | 4 | 20
Working on documentation | 3 | 3 | 6 | 6 | 18
Week 4 |  |  |  |  | 0
Coding the application | 10 | 4 | 10 | 8 | 32
Working on documentation | 2 | 2 | 2 | 2 | 8
Working on Presentation |  |  |  |  | 0
Week 5 |  |  |  |  | 0
Working on Presentation | 2 | 4 |  |  | 6
Prepare for sprint 1 review | 2 | 2 | 2 | 2 | 8
Week 6 |  |  |  |  | 0
Team meeting discuss feedbacks | 2 | 2 | 2 | 2 | 8
Coding the application | 11 | 10 | 11 | 10 | 42
Working on documentation | 3 | 4 | 4 | 3 | 14
Week 7 |  |  |  |  | 0
Finishing up with coding the app | 8 | 7 | 8 | 10 | 33
Testing | 3 | 3 | 3 | 3 | 12
Working on documentation | 4 | 2 | 4 | 3 | 13
Prepare for sprint 2 review | 3 | 3 | 3 | 3 | 12
Working on Presentation |  | 3 |  |  | 3
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Velocity
Sprint 1 velocity | 0.78947
Sprint 2 velocity | 0.57692